## Sheet1
Project Task | Deadline | Notes
Planning and Assessment | 2022-02-16
Discovery & Requirements Gathering
Data Assessment – what data do we have/what data do we need to get? |  | see data dictionary
Technology Set-Up/Access |  | vscode, jupyter extension
Acquire & Load Data |  | Data loaded
Data Preparation | 2022-02-23
Data Profiling & Exploration
Data Cleaning |  | json extracted
Feature Importance |  | shap values for feature importance
Feature Selection
Analysis and Modeling | 2022-03-09
Basic XGBoost Classification Model |  | model fitted
Model Explainability |  | shap values
Data Visualization |  | in notebook visualizations, pbi dashboard
Final Readout | 2022-03-14
Summarize Modeling Results
Deliver Findings & Output
Archive Resources